# Phoenix Engine — Task Breakdown WBS

Document Version: 2.0
Last Updated: 2025-01-21
Classification: Pure Web Scraping Platform — NO Official APIs
Total Tasks: 78
Total Story Points: 520

## Table of Contents

- WBS Summary

- Phase 1 — Core Scraping Engine

- Phase 2 — Platform HTML Scrapers

- Phase 3 — Intelligence Layer

- Phase 4 — Infrastructure

- Phase 5 — Plugin System

- Phase 6 — Integration & Launch

- Dependency Graph

- Resource Loading Chart

- Risk Register

## WBS Summary

| Phase | Name | Tasks | Story Points | Lead Agent |
| --- | --- | --- | --- | --- |
| 1 | Core Scraping Engine | 1.1–1.12 | 135 | Ollama Dev-1 (Alpha) |
| 2 | Platform HTML Scrapers | 2.1–2.24 | 170 | Ollama Dev-2 (Beta) + Dev-3 (Gamma) |
| 3 | Intelligence Layer | 3.1–3.6 | 75 | Ollama Dev-1 (Alpha) |
| 4 | Infrastructure | 4.1–4.15 | 100 | Ollama DevOps |
| 5 | Plugin System | 5.1–5.10 | 65 | Ollama Dev-3 (Gamma) |
| 6 | Integration & Launch | 6.1–6.11 | 55 | All |
|  | TOTAL | 78 | 520 |  |

## Phase 1 — Core Scraping Engine

Phase Lead: Kimi Dev-1 (Alpha)
Phase Goal: Build the foundational scraping primitives that power all platform-specific scrapers
Phase Points: 135

### 1.1 HTTP Scraper Module — Core Client

Points: 13 | Assignee: Kimi Dev-1 | Priority: P0

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 1.1.1 | Async HTTP client setup | 3 | Configure httpx.AsyncClient with connection pooling (limits: 100 max connections, 20 per host), HTTP/2 support, timeout defaults (connect: 5s, read: 30s) |
| 1.1.2 | Custom headers & identity | 2 | Rotating User-Agent strings (Chrome, Firefox, Safari desktop/mobile), Accept-Language negotiation, Referer chain simulation, DNT header |
| 1.1.3 | Response decoding | 2 | Automatic content-encoding handling (gzip, deflate, brotli, zstd), charset detection from headers + meta tags + chardet fallback, binary response handling |
| 1.1.4 | Redirect & URL handling | 2 | Follow redirects (max 10), preserve cookies across redirects, URL normalization (remove tracking params like utm_*, fbclid), canonical URL extraction |
| 1.1.5 | Cookie jar integration | 2 | http.CookieJar integration with external session store, cookie persistence per domain, cookie policy enforcement |
| 1.1.6 | Request signing & integrity | 2 | Request hash for deduplication, response fingerprinting, etag/last-modified support for conditional requests |

Acceptance Criteria: - Successfully fetches 100 test URLs with <2% failure rate - All response decodings produce valid text - Cookies flow correctly through redirects - Unit tests: 95%+ coverage

Depends On: — (foundational)
Blocks: 1.3, 1.4, 1.7, 2.1–2.24

### 1.2 HTML Parsing Engine

Points: 12 | Assignee: Kimi Dev-1 | Priority: P0

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 1.2.1 | BeautifulSoup integration | 3 | BeautifulSoup parser with lxml backend, HTML5lib fallback for malformed HTML, document tree construction, pretty-print debugging output |
| 1.2.2 | lxml integration | 3 | lxml.html parser for speed-critical paths, xpath evaluation engine, cssselect translation (CSS → XPath), HTML cleaner for sanitization |
| 1.2.3 | Document navigation | 2 | DOM traversal helpers (parent, sibling, ancestor selectors), scoped searching (search within subtree), multiple root handling |
| 1.2.4 | Text extraction | 2 | Visible text extraction (exclude script/style), whitespace normalization, entity decoding (&amp; → &), Unicode normalization (NFKC) |
| 1.2.5 | Metadata extraction | 2 | OpenGraph tags (og:title, og:image, etc.), Twitter Cards, standard meta tags (description, keywords, author), JSON-LD structured data parsing, microdata/RDFa extraction |

Acceptance Criteria: - Parses 20 diverse HTML structures (malformed, minified, XHTML, HTML5) - Metadata extraction finds OG tags on 95%+ of pages that have them - Text extraction excludes all script/style content - Benchmark: parse 100KB HTML in <50ms

Depends On: — (foundational)
Blocks: 1.3, 1.4, 1.7

### 1.3 CSS Selector Engine

Points: 11 | Assignee: Kimi Dev-1 | Priority: P0

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 1.3.1 | Core CSS selector support | 3 | Full CSS3 selector support via cssselect: class, ID, attribute, pseudo-class (:nth-child, :not, :contains), descendant, child, sibling combinators |
| 1.3.2 | Selector chain execution | 2 | Execute ordered list of selectors, return first match, track which selector succeeded for health monitoring |
| 1.3.3 | Selector health scoring | 2 | Track success rate per selector over time, detect degradation, auto-report when primary selector success drops below threshold |
| 1.3.4 | Structural selectors | 2 | Position-based selection (first/last/nth element), table cell extraction (row/column semantics), list item enumeration |
| 1.3.5 | Debug & introspection | 2 | Selector tester tool (try selector against HTML), match count reporting, execution trace, visual highlighting in debug output |

Acceptance Criteria: - All CSS3 selectors execute correctly against test HTML - Fallback chain activates when primary selector fails - Health score accurately reflects selector reliability - Debug tool shows selector execution trace

Depends On: 1.2
Blocks: 1.4, 2.1–2.24

### 1.4 XPath Engine

Points: 8 | Assignee: Kimi Dev-1 | Priority: P0

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 1.4.1 | Core XPath support | 3 | Full XPath 1.0 via lxml: axes (ancestor, descendant, following), predicates, functions (contains(), starts-with(), text()), namespace handling |
| 1.4.2 | XPath fallback chains | 2 | Ordered XPath expression lists with fallback, automatic retry on empty result, hybrid CSS+XPath strategies |
| 1.4.3 | Attribute & text extraction | 2 | Extract @href, @src, @datetime attributes, normalize-space text extraction, conditional extraction based on attribute values |
| 1.4.4 | Namespace handling | 1 | XML namespace prefix resolution, default namespace handling, XHTML namespace awareness |

Acceptance Criteria: - XPath 1.0 expressions execute correctly - Fallback chains work as reliably as CSS chains - Attribute extraction handles missing attributes gracefully

Depends On: 1.2, 1.3
Blocks: 1.5, 2.1–2.24

### 1.5 Regex Extraction Helpers

Points: 6 | Assignee: Kimi Dev-1 | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 1.5.1 | Pattern definition DSL | 2 | Named regex groups mapped to fields, pattern composition, pre-compiled pattern cache |
| 1.5.2 | JS variable extraction | 2 | Extract JSON from <script> variables (window._sharedData = {...}), parse ytInitialPlayerResponse, inline JSON-LD from script tags |
| 1.5.3 | Mixed-mode extraction | 2 | Combine regex with DOM parsing (regex to find JS data, then JSON parse), structural regex (multiline HTML patterns) |

Acceptance Criteria: - Successfully extracts embedded JSON from Instagram, YouTube script tags - Named groups produce correctly typed output - Regex cache prevents re-compilation overhead

Depends On: 1.2
Blocks: 2.2, 2.4, 2.6, 2.8

### 1.6 Browser Scraper Module — Playwright Integration

Points: 14 | Assignee: Kimi Dev-1 | Priority: P0

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 1.6.1 | Playwright setup | 3 | Browser launch (Chromium, Firefox, WebKit), headless/headed mode toggle, viewport configuration (1920x1080 default), locale emulation |
| 1.6.2 | Stealth plugin injection | 3 | playwright-stealth integration: patch navigator.webdriver, mock chrome.runtime, fake navigator.plugins and mimeTypes, consistent navigator.languages, webGL fingerprint consistency |
| 1.6.3 | Page automation | 2 | Page navigation with wait conditions (networkidle, domcontentloaded), scroll simulation (smooth scroll, random pauses), click interception, form filling |
| 1.6.4 | Content extraction | 2 | page.content() for full HTML, page.evaluate() for JS data access, element screenshot capture, iframe content access |
| 1.6.5 | Request interception | 2 | Intercept XHR/fetch requests to capture API responses, block unnecessary resources (images, fonts, media) for speed, mock responses for testing |
| 1.6.6 | Error handling | 2 | Timeout recovery, navigation error handling (net::ERR_*), page crash recovery, context isolation on failure |

Acceptance Criteria: - Passes 50 stealth detection tests (FingerprintJS, CreepJS, bot.sannysoft.com) - Successfully renders and extracts JS-heavy sites (React, Vue, Angular SPAs) - Request interception captures XHR payloads correctly - Page crash recovery restarts context automatically

Depends On: — (can parallel with 1.1–1.2)
Blocks: 1.8, 2.1–2.24

### 1.7 Scraping Strategy Selector — HTTP vs Browser Auto-Detect

Points: 10 | Assignee: Kimi Dev-1 | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 1.7.1 | Strategy detection | 3 | Analyze target site characteristics: check if content exists in static HTML vs requires JS execution, detect SPA frameworks (React, Vue, Angular), measure initial HTML vs rendered DOM difference |
| 1.7.2 | Automatic strategy selection | 2 | Rule-based: HTTP first for known static sites, browser for SPAs, hybrid: HTTP for initial + browser for details, ML-based classification (site → strategy mapping) |
| 1.7.3 | Performance optimization | 2 | Cache strategy decisions per domain, periodic re-evaluation, A/B test HTTP vs browser for new domains |
| 1.7.4 | Override system | 2 | Per-site manual override in config, per-task override in API call, force-browser patterns for known tricky sites |
| 1.7.5 | Strategy metrics | 1 | Track success rate per strategy per domain, cost comparison (time, resources), auto-recommendation on strategy failure |

Acceptance Criteria: - Auto-detects correct strategy for 90%+ of test sites - Caches strategy decisions and respects overrides - Metrics show improved success rate vs fixed strategy

Depends On: 1.1, 1.2, 1.6
Blocks: 2.1–2.24

### 1.8 Unified Output Normalizer

Points: 10 | Assignee: Kimi Dev-1 | Priority: P0

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 1.8.1 | Schema definition | 2 | Define ScrapingResult dataclass: url, title, content, author, timestamp, media (images, videos), metadata (platform-specific), raw_html_ref |
| 1.8.2 | Content normalization | 2 | HTML entity decoding, URL normalization (relative → absolute), timestamp normalization (any format → ISO 8601), text cleaning (deduplicate whitespace, strip boilerplate) |
| 1.8.3 | Media handling | 2 | Image URL extraction + proxy-through, video URL detection (MP4, HLS, DASH), thumbnail extraction, media metadata (dimensions when available) |
| 1.8.4 | Platform-specific fields | 2 | Extensible schema for platform additions (e.g., tweet.mentions, video.view_count, post.reactions), validation of required vs optional fields |
| 1.8.5 | Output serialization | 2 | JSON output (default), JSONL for streaming, optional HTML snippet inclusion, provenance tracking (which scraper, which selectors, when) |

Acceptance Criteria: - All scrapers produce identical output schema regardless of source platform - Timestamps consistently normalized to ISO 8601 UTC - Media URLs are absolute and validated (HTTP 200 check) - Unit tests for all normalization paths

Depends On: 1.1–1.5
Blocks: 2.1–2.24, 6.2

### 1.9 Error Handling & Retry Logic

Points: 10 | Assignee: Kimi Dev-1 | Priority: P0

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 1.9.1 | Error classification | 2 | Transient errors (5xx, timeouts, connection reset) vs permanent errors (404, 410, NXDOMAIN), anti-bot indicators (403 with challenge, CAPTCHA signals, rate-limit headers), content errors (empty response, parsing failure) |
| 1.9.2 | Retry strategy | 2 | Exponential backoff: delay = base * (2 ** attempt) + jitter, configurable per domain, max retry attempts (default: 3), per-error-type retry policy |
| 1.9.3 | Circuit breaker | 2 | Track failure rate per domain, open circuit when >80% failure rate in 5-min window, half-open test after cooldown (60s), close on success recovery |
| 1.9.4 | Anti-bot response handling | 2 | Detect Cloudflare challenge pages, detect Akamai/Bot Management blocks, detect CAPTCHA presence, escalate to DevOps for proxy rotation |
| 1.9.5 | Graceful degradation | 2 | Partial extraction (some fields missing), return available data + error details, fallback to cached version if fresh fetch fails |

Acceptance Criteria: - Transient failures retried with exponential backoff - Circuit breaker opens within 30 seconds of sustained failure - Anti-bot detection triggers proxy rotation request - Partial results returned with clear error annotations

Depends On: 1.1
Blocks: 1.10, 2.1–2.24

### 1.10 Audit Logging System

Points: 8 | Assignee: Kimi Dev-1 | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 1.10.1 | Log schema | 2 | Structured JSON log: timestamp, request_id, url, method, headers_sent, response_status, response_size_bytes, duration_ms, scraper_type, selectors_used, fields_extracted, errors, proxy_used |
| 1.10.2 | Log storage | 2 | Async logging to rotating files, optional Redis Stream buffer, log compression (gzip after 24h), retention: hot 7d, warm 30d, cold 90d |
| 1.10.3 | Log querying | 2 | Query by URL pattern, status code range, time range, scraper type, error type, aggregation queries (success rate per domain, avg latency) |
| 1.10.4 | Privacy compliance | 2 | PII redaction in logs, session ID anonymization, configurable retention periods, GDPR-compliant data deletion |

Acceptance Criteria: - Every request creates complete audit log entry - Query interface answers all common diagnostic questions in <2s - Log rotation and compression work automatically - No PII in production logs

Depends On: 1.1, 1.9
Blocks: 4.8, 6.2

### 1.11 Async Pipeline Controller

Points: 12 | Assignee: Kimi Dev-1 | Priority: P0

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 1.11.1 | Task queue | 2 | Async queue with priority levels (high/medium/low), FIFO within priority, task deduplication (URL + params hash), backpressure handling |
| 1.11.2 | Worker pool | 3 | Dynamic worker pool scaling (min: 5, max: 100), per-domain concurrency limits, semaphore-based resource control, worker health monitoring |
| 1.11.3 | Pipeline stages | 2 | Composable pipeline: Fetch → Parse → Extract → Normalize → Output, per-stage timeout and error handling, stage skip on error configuration |
| 1.11.4 | Event system | 2 | Async events: task_started, task_completed, task_failed, circuit_opened, emit to event bus, webhook callback support |
| 1.11.5 | Resource management | 3 | Memory usage monitoring, automatic GC triggers, connection pool management, browser context allocation/deallocation tracking |

Acceptance Criteria: - Handles 1000 concurrent tasks without memory leaks - Pipeline stages compose correctly with proper error propagation - Event system delivers all events within 100ms - Worker pool scales up and down based on queue depth

Depends On: 1.1, 1.6, 1.9
Blocks: 2.1–2.24, 4.3

### 1.12 Regex Pattern Library

Points: 7 | Assignee: Kimi Dev-1 | Priority: P2

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 1.12.1 | Common patterns | 2 | URL pattern matching, email extraction, phone number extraction, date/time pattern matching (multiple formats), hashtag and mention extraction |
| 1.12.2 | Social platform patterns | 2 | Instagram: window._sharedData extraction, X/Twitter: tweet JSON in HTML, TikTok: SIGI_STATE extraction, YouTube: ytInitialPlayerResponse extraction |
| 1.12.3 | Pattern testing | 2 | Pattern validation against 100+ real HTML samples, false positive rate measurement, pattern performance benchmarking |
| 1.12.4 | Pattern registry | 1 | Named registry of patterns, per-domain pattern sets, pattern versioning |

Acceptance Criteria: - Common patterns tested against diverse samples - Platform-specific patterns extract embedded JSON correctly - Pattern registry supports per-domain configuration - <1% false positive rate on text extraction

Depends On: 1.2, 1.5
Blocks: 2.2, 2.4, 2.6, 2.8

## Phase 2 — Platform HTML Scrapers

Phase Lead: Kimi Dev-2 (Beta) + Kimi Dev-3 (Gamma)
Phase Goal: Build platform-specific scrapers using the core engine
Phase Points: 170

### 2.1 Instagram HTML Scraper — Posts

Points: 14 | Assignee: Kimi Dev-2 | Priority: P0

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 2.1.1 | HTML structure analysis | 2 | Analyze Instagram post page DOM: article structure, img tags with srcset, caption location, engagement buttons, timestamp element |
| 2.1.2 | CSS selector mapping | 2 | Primary: article img[srcset] for images, div[class*="caption"] for text, time[datetime] for timestamp, span[class*="likes"] for engagement |
| 2.1.3 | HTTP-based scraper | 2 | Static HTML extraction for public posts, window._sharedData regex extraction from <script>, extract graphql.shortcode_media JSON |
| 2.1.4 | Browser-based scraper | 2 | Playwright for JS-rendered content, scroll to load comments, click “Load more comments” button, handle login-wall detection |
| 2.1.5 | Pagination | 2 | Profile page infinite scroll simulation, detect has_next_page in GraphQL response, cursor-based pagination from end_cursor |
| 2.1.6 | Auth/cookie handling | 2 | Session cookie import from browser, ds_user_id + sessionid validation, handle “Login to continue” interception |
| 2.1.7 | Data normalization | 2 | Map to unified schema: post_url, caption, images[], video_url?, like_count, comment_count, timestamp, username |

Acceptance Criteria: - Extracts post data from 50 public post URLs with >95% field coverage - Handles both image and video posts - Pagination fetches up to 50 posts from profile pages - Graceful handling of login-wall (returns available data)

Depends On: 1.1–1.12
Blocks: 6.2

### 2.2 Instagram HTML Scraper — Reels

Points: 10 | Assignee: Kimi Dev-2 | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 2.2.1 | Reel page analysis | 2 | Reel-specific DOM structure, video player element, audio attribution, effect badges |
| 2.2.2 | Selector mapping | 2 | meta[property="og:video"] for video URL, h1 or caption div for text, view/like/comment counters |
| 2.2.3 | Browser automation | 2 | Playwright required (heavy JS), autoplay handling, video metadata from window._sharedData |
| 2.2.4 | Data extraction | 2 | Video URL, caption, hashtags, view count, like count, comment count, audio info, creator username |
| 2.2.5 | Integration | 2 | Unified output with post scraper, shared auth handling, shared pagination |

Acceptance Criteria: - Extracts reel metadata from 30 public reel URLs - Video URL is direct MP4 link when available - Handles both desktop and mobile reel page layouts

Depends On: 2.1
Blocks: —

### 2.3 Instagram HTML Scraper — Profiles

Points: 10 | Assignee: Kimi Dev-2 | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 2.3.1 | Profile page analysis | 2 | Header section, profile picture, bio, follower/following/post counts, highlight reels |
| 2.3.2 | Selector mapping | 2 | meta[property="og:title"] for name, img[alt*="profile"] for avatar, header section stats spans |
| 2.3.3 | HTTP + browser strategy | 2 | HTTP for basic info from window._sharedData, browser for posts grid with lazy loading |
| 2.3.4 | Profile data extraction | 2 | Username, full name, bio, website link, post count, follower count, following count, profile pic URL |
| 2.3.5 | Recent posts | 2 | Extract recent post grid (up to 12), link to full post scraper for details |

Acceptance Criteria: - Extracts complete profile info from 30 public profiles - Stats counts are numeric (not formatted strings like “1.2M”) - Post grid links resolve correctly

Depends On: 2.1
Blocks: —

### 2.4 X/Twitter HTML Scraper — Tweets

Points: 15 | Assignee: Kimi Dev-2 | Priority: P0

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 2.4.1 | HTML structure analysis | 2 | Tweet article DOM: article[data-testid="tweet"] structure, user info section, tweet text div, media attachments, engagement bar |
| 2.4.2 | CSS selector mapping | 3 | article[data-testid="tweet"] for tweet container, div[data-testid="tweetText"] for text, time[datetime] for timestamp, a[href*="status"] for tweet ID, engagement metrics from span with aria-labels |
| 2.4.3 | HTTP-based scraper | 2 | Extract tweet data from initial HTML, parse window.__INITIAL_STATE__ JSON, extract tweet objects from Redux state |
| 2.4.4 | Browser-based scraper | 3 | Playwright for thread loading, scroll to load reply threads, click “Show more replies”, handle “Show additional replies” modal |
| 2.4.5 | Pagination | 2 | Profile timeline infinite scroll, search results pagination via scroll, cursor extraction from min_position in API responses |
| 2.4.6 | Media extraction | 2 | Image grid detection (1-4 images), video thumbnail + URL, GIF handling, external card previews |
| 2.4.7 | Reply & quote handling | 1 | Distinguish original tweets from replies, detect quote tweets, extract reply-to chain |

Acceptance Criteria: - Extracts 100 tweets with >95% accuracy on text content - Engagement metrics (replies, retweets, likes) are correct - Thread pagination loads full conversation threads - Media URLs extracted for image and video tweets

Depends On: 1.1–1.12
Blocks: 6.2

### 2.5 X/Twitter HTML Scraper — Profiles

Points: 8 | Assignee: Kimi Dev-2 | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 2.5.1 | Profile structure | 2 | Profile header, bio section, pinned tweet, follower/following counts, verified badge detection |
| 2.5.2 | Selector mapping | 2 | div[data-testid="UserName"] for name, div[data-testid="UserDescription"] for bio, profile image, stats from a[href*="verified_followers"] etc. |
| 2.5.3 | Data extraction | 2 | Username, display name, bio, location, website, join date, follower count, following count, tweet count, profile image |
| 2.5.4 | Recent tweets | 2 | Link to tweet scraper for timeline extraction, pinned tweet identification |

Acceptance Criteria: - Extracts complete profile from 30 public profiles - Verified badge status detected - Stats are numeric, not formatted

Depends On: 2.4
Blocks: —

### 2.6 TikTok HTML Scraper — Videos

Points: 14 | Assignee: Kimi Dev-2 | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 2.6.1 | HTML structure analysis | 2 | TikTok video page: SIGI_STATE in <script>, video container, caption section, sound info, engagement metrics |
| 2.6.2 | CSS selector mapping | 2 | div[data-e2e="title"] for caption, strong[data-e2e="like-count"] for likes, div[data-e2e="browse-video"] for video |
| 2.6.3 | Browser-based scraper | 3 | Playwright required (heavy anti-bot), request interception for video CDN URLs, SIGI_STATE extraction from script tag |
| 2.6.4 | HTTP-based scraper | 2 | Extract metadata from <meta> tags (og:title, og:description), parse embedded JSON when available |
| 2.6.5 | Video metadata | 2 | Video URL (direct MP4 or HLS), caption text, hashtags, creator info, sound/music attribution, duration |
| 2.6.6 | Engagement extraction | 2 | Like count, comment count, share count, view count (if visible), bookmark count |
| 2.6.7 | Pagination | 1 | Profile video grid pagination via scroll, related videos sidebar |

Acceptance Criteria: - Extracts video metadata from 30 public TikTok URLs - Direct video URL or HLS playlist extracted - Hashtags parsed as individual items - Handles both desktop and mobile layouts

Depends On: 1.1–1.12
Blocks: —

### 2.7 TikTok HTML Scraper — Profiles

Points: 8 | Assignee: Kimi Dev-2 | Priority: P2

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 2.7.1 | Profile analysis | 2 | Profile header, avatar, bio stats, video grid layout, follower/following/like counts |
| 2.7.2 | Selector mapping | 2 | h1[data-e2e="user-title"] for username, h2[data-e2e="user-subtitle"] for nickname, stats from strong[data-e2e="following-count"] etc. |
| 2.7.3 | Data extraction | 2 | Username, nickname, bio, follower count, following count, total likes, profile pic, verified status |
| 2.7.4 | Video grid | 2 | Extract video list from profile (links + thumbnails + view counts), pagination via infinite scroll |

Acceptance Criteria: - Extracts profile info from 20 public TikTok profiles - Video grid lists up to 30 videos with thumbnails - Stats are numeric

Depends On: 2.6
Blocks: —

### 2.8 LinkedIn HTML Scraper — Public Posts

Points: 12 | Assignee: Kimi Dev-2 | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 2.8.1 | HTML structure analysis | 2 | Public post page: article or main content div, author info section, post text, engagement bar, comment section |
| 2.8.2 | CSS selector mapping | 2 | .feed-shared-update-v2__description for text, .feed-shared-actor__name for author, .social-details-social-counts for engagement |
| 2.8.3 | HTTP-based scraper | 2 | Extract from public view (no login), parse <code> blocks containing JSON data, <meta> tag extraction |
| 2.8.4 | Browser-based scraper | 2 | Playwright for full rendering, comment loading via scroll, “Load more comments” click |
| 2.8.5 | Data extraction | 2 | Post text, author name, author profile URL, timestamp, like count, comment count, share count, media attachments |
| 2.8.6 | Public vs auth-walled | 2 | Detect login wall (redirect to login page), return available data + error, handle “Sign in to view” gracefully |

Acceptance Criteria: - Extracts data from 30 public LinkedIn post URLs - Graceful handling of login-wall content - Author info and engagement metrics accurate - Only public posts — no authenticated scraping

Depends On: 1.1–1.12
Blocks: —

### 2.9 LinkedIn HTML Scraper — Public Profiles

Points: 10 | Assignee: Kimi Dev-2 | Priority: P2

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 2.9.1 | Profile structure | 2 | Public profile layout: top card, about section, experience section, education section |
| 2.9.2 | Selector mapping | 2 | .top-card-layout__title for name, .top-card-layout__headline for headline, section.experience for work history |
| 2.9.3 | Data extraction | 2 | Name, headline, location, about summary, current position, experience list, education list, skills (if visible) |
| 2.9.4 | Public visibility only | 2 | Respect public profile visibility, detect partial visibility (“Sign in to see full profile”), return available sections only |
| 2.9.5 | Browser handling | 2 | Playwright for sections requiring interaction (“Show more” clicks), scroll to load all experience entries |

Acceptance Criteria: - Extracts available data from 20 public profiles - Respects visibility limits (no auth bypass attempts) - All available sections extracted completely

Depends On: 2.8
Blocks: —

### 2.10 Facebook HTML Scraper — Public Posts

Points: 13 | Assignee: Kimi Dev-3 | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 2.10.1 | HTML structure analysis | 2 | Facebook post HTML: div[role="article"] structure, story container, user header, content area, engagement footer |
| 2.10.2 | CSS selector mapping | 2 | div.story_body_container for content, h3 or h4 for author name, span[data-ft] for timestamp, span[aria-label] for reactions |
| 2.10.3 | Browser-based scraper | 3 | Playwright required (heavy JS rendering), handle initial page load delay, scroll-triggered content loading |
| 2.10.4 | HTTP-based scraper | 2 | Basic meta tag extraction when available, parse server-rendered HTML fragments |
| 2.10.5 | Data extraction | 2 | Post text, author name, author URL, timestamp, reaction counts (like, love, wow, etc.), share count, comment count, media |
| 2.10.6 | Anti-bot handling | 2 | Detect checkpoint/interstitial pages, handle “Log in to continue” gracefully, rate limit detection |

Acceptance Criteria: - Extracts post data from 30 public Facebook post URLs - Handles both photo and text posts - Graceful handling of login checkpoints - Reaction breakdown (not just total) when visible

Depends On: 1.1–1.12
Blocks: —

### 2.11 Facebook HTML Scraper — Pages

Points: 10 | Assignee: Kimi Dev-3 | Priority: P2

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 2.11.1 | Page structure | 2 | Page header, profile picture, cover photo, about section, page category, follower count |
| 2.11.2 | Selector mapping | 2 | h1 for page name, div[role="main"] for content, about section divs |
| 2.11.3 | Data extraction | 2 | Page name, category, follower count, like count, website, phone, address (if public), about text |
| 2.11.4 | Recent posts | 2 | Extract recent posts timeline, link to post scraper for detail |
| 2.11.5 | Browser handling | 2 | Playwright for full rendering, handle page tabs (About, Posts, Photos) |

Acceptance Criteria: - Extracts page info from 20 public pages - Timeline shows up to 10 recent posts - Stats are numeric

Depends On: 2.10
Blocks: —

### 2.12 YouTube HTML Scraper — Video Metadata

Points: 13 | Assignee: Kimi Dev-3 | Priority: P0

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 2.12.1 | HTML structure analysis | 2 | Video watch page: ytInitialPlayerResponse in <script>, ytInitialData for page structure, meta tags, video player container |
| 2.12.2 | CSS selector mapping | 2 | meta[name="title"] for title, span.yt-formatted-string for description, yt-formatted-string[aria-label] for view count |
| 2.12.3 | Embedded JSON extraction | 3 | Regex extract ytInitialPlayerResponse from script tag, parse as JSON, extract: videoDetails.title, videoDetails.author, videoDetails.viewCount, microformat.playerMicroformatRenderer |
| 2.12.4 | HTTP-based scraper | 3 | Primary path: extract embedded JSON from static HTML, no browser needed for basic metadata, secondary: meta tag fallback |
| 2.12.5 | Browser-based scraper | 2 | Playwright for comments section, description “Show more” expansion, related videos sidebar |
| 2.12.6 | Data extraction | 1 | Title, description, channel name, channel URL, view count, like count, publish date, tags, category, duration, thumbnail URLs |

Acceptance Criteria: - Extracts metadata from 50 public video URLs with >98% accuracy - ytInitialPlayerResponse extraction works on all video pages - View counts are numeric (not formatted) - Thumbnail URLs at multiple resolutions

Depends On: 1.1–1.12, 1.5, 1.12
Blocks: 2.13, 6.2

### 2.13 YouTube HTML Scraper — Transcript Extraction

Points: 10 | Assignee: Kimi Dev-3 | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 2.13.1 | Transcript location | 2 | Parse ytInitialPlayerResponse.videoDetails.captionTracks, find caption track URLs (timedtext API), auto-generated vs manual caption detection |
| 2.13.2 | Transcript fetching | 2 | Fetch caption track XML, parse <text> elements with start and dur attributes, handle multiple language tracks |
| 2.13.3 | Format conversion | 2 | Convert to SRT format (sequential numbering, timecode formatting), convert to plain text with timestamps, convert to JSON with timing info |
| 2.13.4 | Language handling | 2 | Auto-detect available languages, default to auto-generated captions, language parameter support |
| 2.13.5 | Error handling | 2 | Handle videos with captions disabled, handle “unavailable in your country”, fallback to description text if no captions |

Acceptance Criteria: - Extracts transcripts from 30 videos that have captions - Supports both auto-generated and manual captions - SRT output has correct timecodes - Handles disabled captions gracefully

Depends On: 2.12
Blocks: —

### 2.14 YouTube HTML Scraper — Channels

Points: 10 | Assignee: Kimi Dev-3 | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 2.14.1 | Channel structure | 2 | Channel page layout, header with banner, avatar, channel name, subscriber count, video tab |
| 2.14.2 | Selector mapping | 2 | meta[property="og:title"] for name, yt-formatted-string#subscriber-count for subs, div#description-container for description |
| 2.14.3 | ytInitialData extraction | 2 | Parse ytInitialData for channel metadata, header.c4TabbedHeaderRenderer for stats, metadata.channelMetadataRenderer for details |
| 2.14.4 | Data extraction | 2 | Channel name, handle, description, subscriber count, video count, total views, join date, links, avatar URL, banner URL |
| 2.14.5 | Video list | 2 | Extract recent uploads (video IDs, titles, thumbnails, view counts, publish dates), pagination via scroll/infinite load |

Acceptance Criteria: - Extracts channel info from 20 public channels - Video list shows up to 30 recent uploads - Stats are numeric

Depends On: 2.12
Blocks: —

### 2.15 YouTube HTML Scraper — Comments

Points: 8 | Assignee: Kimi Dev-3 | Priority: P2

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 2.15.1 | Comments section | 2 | Parse ytInitialData for continuation token, extract top-level comments and replies |
| 2.15.2 | Browser automation | 2 | Scroll to load more comments, click “Show more replies”, sort by top/newest |
| 2.15.3 | Data extraction | 2 | Comment text, author name, author channel URL, timestamp, like count, reply count, is_reply flag |
| 2.15.4 | Pagination | 2 | Extract continuation tokens for pagination, configurable max comments to fetch |

Acceptance Criteria: - Extracts comments from 15 videos - Supports top-level and reply comments - Configurable comment limit

Depends On: 2.12
Blocks: —

### 2.16 Generic Web Scraper — Universal Article Extraction

Points: 15 | Assignee: Kimi Dev-3 | Priority: P0

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 2.16.1 | Content detection | 3 | Algorithm to detect main content area vs boilerplate (readability-style), density-based scoring, link-to-text ratio analysis, structural heuristics |
| 2.16.2 | Article extraction | 3 | Extract article title (<h1> or OG title), author detection (rel=“author”, meta tags, byline patterns), publish date extraction (meta tags, JSON-LD, structural patterns), article body (longest text block with paragraph structure) |
| 2.16.3 | Universal selectors | 2 | Platform-agnostic fallback chain: OG tags → semantic HTML (<article>, <main>) → readability algorithm → largest text block |
| 2.16.4 | Multi-site testing | 3 | Test on 50 diverse sites: news sites (CNN, BBC, NYT), blogs (Medium, Substack), corporate sites, forums — without any site-specific configuration |
| 2.16.5 | Edge case handling | 2 | Handle: multi-page articles, AMP pages, paywall detection, login-walled content, empty/error pages, non-article pages (redirect to generic metadata extraction) |
| 2.16.6 | Quality scoring | 2 | Content quality score (length, structure, metadata completeness), confidence score for each extracted field, recommendation when manual review needed |

Acceptance Criteria: - Successfully extracts articles from 50 diverse sites - Title, author, date, body extracted with >90% accuracy - No site-specific configuration required - Quality score accurately reflects extraction confidence

Depends On: 1.1–1.12
Blocks: 5.4, 6.2

### 2.17 Generic Web Scraper — Metadata Extraction

Points: 8 | Assignee: Kimi Dev-3 | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 2.17.1 | Meta tag extraction | 2 | Standard meta tags, OpenGraph tags, Twitter Cards, JSON-LD structured data, Dublin Core |
| 2.17.2 | Link extraction | 2 | All links on page (href + anchor text), external vs internal classification, canonical URL detection |
| 2.17.3 | Image extraction | 2 | All images (src + alt text), filter by size (exclude tiny icons), hero image detection |
| 2.17.4 | Structured data | 2 | Schema.org parsing (Article, Person, Organization, VideoObject, etc.), RDFa parsing, microdata extraction |

Acceptance Criteria: - Extracts complete metadata from 30 diverse pages - Structured data parsed for all common schema types - Link classification (internal/external) is accurate

Depends On: 2.16
Blocks: —

### 2.18–2.24 Pagination Handlers (Shared Component)

Points: 14 | Assignee: Kimi Dev-2 + Dev-3 | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 2.18 | Infinite scroll handler | 2 | Detect scroll-triggered loading (mutation observer pattern), simulate scroll events, detect “no more content” signal, configurable max scroll depth |
| 2.19 | Load-more button handler | 2 | Detect “Load more” / “Show more” buttons, click via Playwright, retry on stale element, detect button disappearance |
| 2.20 | Page number handler | 2 | URL pattern pagination (?page=2, /page/2/), next/previous link detection, page count estimation, sequential or parallel fetching |
| 2.21 | Cursor/token pagination | 2 | Extract continuation tokens from JS variables or API responses (cursor, offset, token), append to subsequent requests, detect end-of-list |
| 2.22 | Pagination unification | 2 | Unified Paginator interface: has_more(), next_page(), get_all(), auto-detect pagination type per page |
| 2.23 | Pagination metrics | 2 | Track items per page, total items fetched, pagination failure rate, adaptive fetch sizing |
| 2.24 | Pagination tests | 2 | Test each pagination type with recorded HTML fixtures, simulate slow loading, test max depth enforcement |

Acceptance Criteria: - All 4 pagination types work correctly - Unified interface works across all platform scrapers - Max depth and item limits enforced - Tests cover edge cases (empty pages, stuck loaders)

Depends On: 1.6, 1.11
Blocks: 2.1–2.17

## Phase 3 — Intelligence Layer

Phase Lead: Kimi Dev-1 (Alpha)
Phase Goal: AI-assisted capabilities for resilient and smart scraping
Phase Points: 75

### 3.1 AI-Assisted HTML Structure Analysis

Points: 15 | Assignee: Kimi Dev-1 | Priority: P2

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 3.1.1 | DOM feature extraction | 3 | Extract structural features from DOM: tag distribution, class name patterns, id naming conventions, nesting depth, semantic tag usage |
| 3.1.2 | Content region detection | 3 | ML-based main content region detection using features: text density, link density, visual position hints, tag semantics |
| 3.1.3 | Dynamic content detection | 3 | Detect if content is JS-rendered: compare static HTML vs rendered DOM, detect framework signatures (React data-reactroot, Vue __vue__, Angular ng-*) |
| 3.1.4 | Structure change detection | 3 | Compare current DOM structure with known pattern, detect class name changes, detect element reordering, alert on significant structure drift |
| 3.1.5 | Selector recommendation | 3 | Given target content type (post, article, product), recommend selector strategy based on DOM analysis, suggest robust selectors over fragile ones |

Acceptance Criteria: - Content region detection finds main content on 90%+ of test pages - Framework detection correctly identifies React/Vue/Angular/None - Structure change detection alerts within 1 hour of layout changes - Selector recommendations are more robust than baseline

Depends On: 1.2, 1.3, 1.7
Blocks: 3.2, 3.3

### 3.2 Smart Selector Fallback Chains

Points: 13 | Assignee: Kimi Dev-1 | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 3.2.1 | Fallback chain definition | 2 | Declarative fallback chains: primary → secondary → tertiary → heuristic, each entry with strategy (CSS/XPath/regex/ML) and timeout |
| 3.2.2 | Chain execution engine | 2 | Execute chains in order, track which selector succeeded, record success distribution for optimization, parallel execution of multiple chains |
| 3.2.3 | Auto-fallback generation | 3 | Generate fallback selectors automatically from successful primary selector: class-only fallback, tag+parent fallback, positional fallback, content-based fallback |
| 3.2.4 | Chain optimization | 3 | Machine learning on selector success rates: reorder chain based on empirical success, remove consistently failing selectors, add newly discovered successful selectors |
| 3.2.5 | Fallback metrics | 3 | Track fallback activation rate per field, alert when primary selector success < 90%, recommend chain updates |

Acceptance Criteria: - Fallback chains activate transparently when primary fails - Auto-generated fallbacks are more robust than hand-written ones - Chain optimization improves success rate by >5% over static chains - Metrics accurately track selector health

Depends On: 1.3, 1.4, 3.1
Blocks: 3.4

### 3.3 Content Type Classifier

Points: 12 | Assignee: Kimi Dev-1 | Priority: P2

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 3.3.1 | Feature extraction | 2 | HTML-based features: meta tags, OG type, structured data, URL patterns, domain, path structure |
| 3.3.2 | Classifier training | 3 | Train on labeled dataset: article, product, profile, post, video, forum_thread, homepage, category_page, using features + light ML model |
| 3.3.3 | Rule-based classifier | 3 | URL pattern rules (/p/ = Instagram post, /status/ = tweet, /watch?v= = YouTube video), meta tag rules (og:type mapping), domain-specific rules |
| 3.3.4 | Hybrid classification | 2 | Combine rule-based (fast, deterministic) with ML-based (accurate on edge cases), confidence scoring, human-review queue for low-confidence |
| 3.3.5 | Classification-driven extraction | 2 | Route to appropriate scraper based on classification, select selector set based on content type, adjust strategy (HTTP vs browser) based on type |

Acceptance Criteria: - Classifies content type with >95% accuracy on test set - Rule-based covers 80%+ of common cases instantly - ML handles edge cases and new platforms - Classification correctly routes to appropriate scraper

Depends On: 1.2, 1.8
Blocks: 3.5

### 3.4 Anti-Bot Detection & Response

Points: 15 | Assignee: Kimi Dev-1 + DevOps | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 3.4.1 | Block page detection | 3 | Detect known block pages: Cloudflare challenge (IUAM, CAPTCHA), Akamai Bot Manager, PerimeterX/Human, DataDome, custom WAF pages |
| 3.4.2 | Response pattern analysis | 3 | Analyze response patterns: HTTP 403 with challenge cookie, 429 rate limit, redirect to /challenge, response time anomalies (block pages load fast), content length anomalies |
| 3.4.3 | Fingerprint randomization | 3 | Rotate: User-Agent (consistent with OS), Accept headers, viewport size, timezone, language, canvas/WebGL noise (via Playwright stealth) |
| 3.4.4 | Response strategy | 3 | On block detection: rotate proxy, rotate session, increase delay, switch to browser mode, escalate to manual review after N failures |
| 3.4.5 | Anti-bot metrics | 3 | Track block rate per domain per strategy, proxy block rate, session validity duration, time-to-block metrics |

Acceptance Criteria: - Detects all major anti-bot systems with >95% accuracy - Automatic response reduces block rate by >80% - Fingerprint rotation maintains consistency per session - Metrics dashboard shows anti-bot status

Depends On: 1.6, 1.9, 3.2, 4.2, 4.3
Blocks: 6.2

### 3.5 Automatic Scraper Repair

Points: 12 | Assignee: Kimi Dev-1 | Priority: P2

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 3.5.1 | Failure detection | 2 | Detect when scraper returns empty/malformed data, compare output schema completeness against baseline, detect field-level null rate spikes |
| 3.5.2 | HTML diff analysis | 3 | Compare current HTML with last-known-good HTML, identify changed class names, moved elements, renamed attributes, structural changes |
| 3.5.3 | Selector regeneration | 3 | Generate new selector candidates from current HTML, rank by stability (avoid generated class names), test candidates against current HTML |
| 3.5.4 | Repair validation | 2 | Run repaired scraper against test fixtures, validate output schema completeness, regression test against known URLs |
| 3.5.5 | Human review queue | 2 | Queue suggested repairs for review, highlight confidence level, auto-apply high-confidence repairs after validation |

Acceptance Criteria: - Detects scraper breakage within 1 hour - Generates repair suggestions with >70% accuracy - Validated repairs pass all regression tests - Human review queue is manageable (< 10 items/day)

Depends On: 3.1, 3.2
Blocks: —

### 3.6 Adaptive Rate Limiting

Points: 8 | Assignee: Kimi Dev-1 + DevOps | Priority: P2

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 3.6.1 | Response-based adaptation | 2 | Monitor response codes: increase delay on 429, decrease delay on consistent 200s, detect soft blocks (200 with empty content) |
| 3.6.2 | Domain profiling | 2 | Build per-domain rate tolerance profile, learn from historical patterns, share profiles across instances |
| 3.6.3 | Aggressive site detection | 2 | Detect sites with strict rate limiting early, classify sites by tolerance (lenient/moderate/strict), apply appropriate default delays |
| 3.6.4 | Adaptive algorithm | 2 | Gradient-based rate adjustment: small increments on success, larger decrements on failure, floor/ceiling constraints, jitter addition |

Acceptance Criteria: - Adapts to site tolerance within 10 requests - No IP bans during normal operation - Throughput optimized per domain - Shared profiles improve cold-start behavior

Depends On: 1.9, 4.5
Blocks: —

## Phase 4 — Infrastructure

Phase Lead: Kimi DevOps
Phase Goal: Build resilient, scalable, observable scraping infrastructure
Phase Points: 100

### 4.1 Cookie & Session Manager

Points: 12 | Assignee: Kimi DevOps | Priority: P0

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 4.1.1 | Session storage | 3 | SQLite schema for sessions: id, domain, cookies_json (encrypted), created_at, last_used, use_count, is_valid, AES-256-GCM encryption with key rotation |
| 4.1.2 | Cookie jar management | 2 | Per-domain cookie jars, cookie expiration handling, secure flag enforcement, SameSite handling, automatic cookie refresh detection |
| 4.1.3 | Session rotation | 2 | Round-robin session selection per domain, session cooldown (min time between uses), session retirement after max uses, health-based selection (prefer valid sessions) |
| 4.1.4 | Session validation | 2 | Validate session by making test request, detect logout/session expiry, auto-mark invalid sessions, re-validation schedule |
| 4.1.5 | Import/export | 2 | Import cookies from browser (Netscape format, JSON), export for backup, session migration between instances |
| 4.1.6 | Privacy & security | 1 | Encrypted at rest, secure key management (environment variable), audit log of session access, automatic expiration |

Acceptance Criteria: - Session storage with AES-256 encryption - Rotation prevents session exhaustion - Invalid sessions detected and retired automatically - Import from Chrome/Firefox cookie format

Depends On: — (foundational)
Blocks: 2.1–2.24, 4.3

### 4.2 Proxy Management Infrastructure

Points: 12 | Assignee: Kimi DevOps | Priority: P0

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 4.2.1 | Proxy pool | 3 | Support: HTTP/HTTPS proxies, SOCKS4/5 proxies, authenticated proxies (user:pass), proxy chain support, pool configuration via file/ENV/API |
| 4.2.2 | Health checking | 2 | Periodic proxy health checks (HTTP GET to known endpoint), response time measurement, anonymity verification (header leak detection), geo-location verification |
| 4.2.3 | Rotation strategy | 2 | Per-request rotation, sticky sessions (same proxy for domain session), least-recently-used, performance-based selection (lowest latency), failure-based exclusion |
| 4.2.4 | Geographic targeting | 2 | Target specific countries/regions, ASN targeting, city-level targeting, fallback chain for geo preferences |
| 4.2.5 | Failover handling | 2 | Automatic failover on proxy failure, retry with different proxy, mark proxy as failed after N consecutive failures, automatic recovery testing |
| 4.2.6 | Proxy metrics | 1 | Success rate per proxy, average latency, bytes transferred, failure reasons, cost tracking |

Acceptance Criteria: - Pool of 50+ proxies manageable - Health check marks failed proxies within 60s - Rotation prevents IP-based blocking - Geographic targeting works accurately

Depends On: — (foundational)
Blocks: 2.1–2.24, 3.4

### 4.3 Browser Instance Pool Management

Points: 10 | Assignee: Kimi DevOps | Priority: P0

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 4.3.1 | Pool architecture | 2 | Context-per-task isolation, persistent browser process, dynamic pool sizing (min: 2, max: 20), queue for browser requests |
| 4.3.2 | Lifecycle management | 2 | Browser process start/stop/restart, automatic restart on crash, memory leak prevention (periodic context purge), graceful shutdown |
| 4.3.3 | Context fingerprinting | 2 | Per-context fingerprint configuration: viewport, user-agent, locale, timezone, color scheme, consistent fingerprint per session |
| 4.3.4 | Resource limits | 2 | Per-context memory limits, page count limits, timeout enforcement, CPU usage monitoring |
| 4.3.5 | Pool monitoring | 2 | Active contexts count, queue depth, average wait time, context creation time, crash rate |

Acceptance Criteria: - 20 concurrent browser contexts without crashes - Context isolation (cookies, localStorage separated) - Automatic restart on memory >500MB per context - Wait time <5s when pool at capacity

Depends On: 1.6, 4.1
Blocks: 2.1–2.24

### 4.4 Browser Stealth Configuration

Points: 8 | Assignee: Kimi DevOps | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 4.4.1 | Stealth plugin management | 2 | playwright-stealth integration, custom stealth scripts, canvas fingerprint noise, WebGL vendor consistency |
| 4.4.2 | Consistent identity | 2 | Per-context consistent fingerprint: same User-Agent + viewport + locale throughout session, browser-level consistency (plugins, fonts, canvas) |
| 4.4.3 | Detection evasion | 2 | navigator.webdriver = false, mock chrome.runtime, consistent navigator.plugins, Permission API mock, WebDriver property removal |
| 4.4.4 | Stealth testing | 2 | Automated testing against fingerprinting libraries (FingerprintJS, CreepJS, BotD), score tracking per configuration, A/B testing stealth configurations |

Acceptance Criteria: - Passes FingerprintJS with uniqueness < 1 in 1000 - Consistent identity throughout session - All known automation leaks patched - Stealth score tracked over time

Depends On: 1.6, 4.3
Blocks: 2.1–2.24

### 4.5 Rate Controller

Points: 10 | Assignee: Kimi DevOps | Priority: P0

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 4.5.1 | Per-domain configuration | 2 | Configurable: requests/second, concurrent requests, delay between requests, burst allowance, daily/hourly quotas |
| 4.5.2 | robots.txt compliance | 2 | Fetch and parse robots.txt, respect Crawl-delay, respect Disallow directives, cache robots.txt per domain |
| 4.5.3 | Distributed coordination | 2 | Redis-based distributed rate limiting, consistent across instances, token bucket algorithm, sliding window counting |
| 4.5.4 | Adaptive adjustment | 2 | Auto-increase delay on 429 responses, auto-decrease on consistent success, integrate with Phase 3.6 adaptive rate limiting |
| 4.5.5 | Rate metrics | 2 | Current RPS per domain, throttle events, queue wait time, quota exhaustion tracking |

Acceptance Criteria: - Respects robots.txt for all domains - Per-domain rate limits enforced accurately - Distributed rate limiting consistent across 5 instances - No rate limit violations during normal operation

Depends On: — (foundational)
Blocks: 2.1–2.24, 3.6

### 4.6 Raw HTML Archive Storage

Points: 10 | Assignee: Kimi DevOps | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 4.6.1 | Storage format | 2 | Raw HTML + metadata stored together, zstd compression (ratio > 5:1), content-addressable (SHA-256 hash), deduplication |
| 4.6.2 | Retention policies | 2 | Tiered storage: hot (SSD, 7 days), warm (object storage, 30 days), cold (archive, 90 days), configurable per domain |
| 4.6.3 | Query interface | 2 | Query by URL, time range, domain, content hash, response status, full-text search on extracted text |
| 4.6.4 | Backup & recovery | 2 | Daily incremental backups, point-in-time recovery, cross-region replication for critical data, backup integrity verification |
| 4.6.5 | Storage metrics | 2 | Storage used per domain, compression ratio, dedup savings, retrieval latency, growth rate |

Acceptance Criteria: - Compression ratio > 5:1 - Retrieval latency <100ms for hot storage - Deduplication prevents identical re-storage - Backup recovery tested monthly

Depends On: 1.10
Blocks: 6.2

### 4.7 Structured Output Storage

Points: 8 | Assignee: Kimi DevOps | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 4.7.1 | JSON output storage | 2 | Structured scraping results in JSON, schema validation, indexed fields for querying, versioned schema |
| 4.7.2 | Export system | 2 | JSON export (default), CSV export (tabular data), JSONL export (streaming), XML export, Parquet export (analytics) |
| 4.7.3 | Query API | 2 | Filter by URL, domain, date range, content type, full-text search on content, aggregation queries |
| 4.7.4 | Data retention | 2 | Configurable retention per project, automatic purging, GDPR deletion support, data export for portability |

Acceptance Criteria: - All export formats produce valid output - Query API responds in <2s for common queries - Schema validation rejects invalid data - Retention policy automatically enforced

Depends On: 1.8
Blocks: 6.2

### 4.8 Monitoring & Alerting

Points: 10 | Assignee: Kimi DevOps | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 4.8.1 | Metrics collection | 2 | Collect: requests/min, success rate, latency (p50/p95/p99), bytes transferred, selector success rate, proxy health, browser pool utilization |
| 4.8.2 | Dashboard | 2 | Grafana/Prometheus dashboard: per-domain status, overall health, top errors, queue depth, resource usage, trend graphs |
| 4.8.3 | Alerting rules | 2 | Alerts: success rate < 95%, latency p95 > 10s, queue depth > 1000, browser crash rate > 5%, proxy failure rate > 20%, disk usage > 80% |
| 4.8.4 | Log aggregation | 2 | Centralized log collection (Loki/ELK), structured log parsing, log-based alerting, log correlation across services |
| 4.8.5 | Health checks | 2 | /health endpoint, readiness/liveness probes, dependency health checks (Redis, storage), automated health reports |

Acceptance Criteria: - Dashboard refreshes within 5 seconds - Alerts fire within 30 seconds of threshold breach - All logs queryable within 1 minute of generation - Health endpoint accurately reflects system state

Depends On: 1.10, 4.6, 4.7
Blocks: 6.2

### 4.9 Docker Deployment

Points: 8 | Assignee: Kimi DevOps | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 4.9.1 | Container images | 2 | Multi-stage Dockerfile (builder → runtime), Playwright browser installation, minimal attack surface image, image size < 500MB |
| 4.9.2 | Docker Compose | 2 | docker-compose.yml with all services, environment variable configuration, volume mounts for persistent data, network isolation |
| 4.9.3 | Health checks | 2 | Container health checks, restart policies, resource limits (CPU, memory), graceful shutdown handling |
| 4.9.4 | Environment parity | 2 | Dev/staging/prod parity via environment variables, feature flags, configuration management, secret management |

Acceptance Criteria: - docker-compose up starts full stack - Container starts in <30 seconds - Health checks pass within 60 seconds - Graceful shutdown preserves in-flight tasks

Depends On: 4.1–4.8
Blocks: 6.4

### 4.10 CI/CD Pipeline

Points: 6 | Assignee: Kimi DevOps | Priority: P2

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 4.10.1 | Build pipeline | 2 | Automated build on push, lint (ruff, mypy), unit tests, integration tests, Docker image build, security scan |
| 4.10.2 | Test automation | 2 | Run all test suites in CI, HTML fixture validation, selector regression tests, browser scraper tests with Playwright |
| 4.10.3 | Deployment | 2 | Automated staging deployment, manual production gate, blue-green deployment, rollback capability |

Acceptance Criteria: - Build completes in <10 minutes - All tests pass before deployment - Staging auto-deploys on green build - Rollback completes in <5 minutes

Depends On: 4.9
Blocks: 6.4

### 4.11–4.15 Security & Compliance

Points: 14 | Assignee: Kimi DevOps | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 4.11 | Secret management | 3 | API keys, proxy credentials, encryption keys in environment variables or secret manager, rotation schedule, audit access |
| 4.12 | TLS/SSL | 2 | All external communication over HTTPS, certificate validation, custom CA support for proxies, cipher suite configuration |
| 4.13 | Input validation | 3 | URL validation (scheme, host, path), sanitize all inputs, prevent SSRF (block internal IPs, localhost), rate limit on API endpoints |
| 4.14 | Audit trail | 3 | All operations logged with timestamp + actor + action + result, tamper-resistant storage, retention compliance, audit report generation |
| 4.15 | GDPR/privacy | 3 | Data minimization (only collect requested fields), retention limits, data deletion API, privacy impact assessment, user consent tracking |

Acceptance Criteria: - No secrets in code or logs - SSRF prevention blocks all internal IP requests - Audit trail is complete and tamper-resistant - GDPR deletion completes within 30 days request

Depends On: 4.9
Blocks: 6.4

## Phase 5 — Plugin System

Phase Lead: Kimi Dev-3 (Gamma)
Phase Goal: Build extensible plugin architecture for custom scrapers
Phase Points: 65

### 5.1 Plugin Interface Design

Points: 10 | Assignee: Kimi Dev-3 | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 5.1.1 | Abstract base class | 2 | BaseScraperPlugin with methods: can_handle(url), scrape(url), get_selectors(), get_config(), type hints, docstring standards |
| 5.1.2 | URL pattern matching | 2 | Pattern registration: regex patterns, glob patterns, domain matching, path prefix matching, priority ordering |
| 5.1.3 | Selector registration | 2 | Declarative selector sets: CSS selectors, XPath expressions, regex patterns, fallback chains, selector documentation |
| 5.1.4 | Configuration schema | 2 | Per-plugin config: rate limits, auth requirements, browser vs HTTP preference, custom headers, timeout overrides |
| 5.1.5 | Lifecycle hooks | 2 | on_load(), before_scrape(), after_scrape(), on_error(), on_unload() hooks for plugin lifecycle management |

Acceptance Criteria: - Base class is well-documented and type-hinted - URL pattern matching resolves correct plugin for test URLs - Selector registration supports all selector types - Lifecycle hooks fire in correct order

Depends On: 1.1–1.12
Blocks: 5.2–5.10

### 5.2 Plugin Loader & Registration

Points: 10 | Assignee: Kimi Dev-3 | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 5.2.1 | Discovery mechanism | 2 | Auto-discover plugins from directory, package-based plugin loading, entry point registration (setup.py entry_points), explicit registration API |
| 5.2.2 | Dependency injection | 2 | Inject core engine components (HTTP client, browser pool, selector engine), inject config, inject logger, inject audit trail |
| 5.2.3 | Hot reload | 2 | Watch plugin files for changes, reload without engine restart, graceful degradation on reload failure, version tracking |
| 5.2.4 | Validation framework | 2 | Validate plugin on load: URL patterns compile, selectors are valid, required methods implemented, config schema validates |
| 5.2.5 | Plugin registry | 2 | In-memory registry of loaded plugins, conflict detection (multiple plugins for same URL), priority resolution, listing/query API |

Acceptance Criteria: - Plugin discovered and loaded automatically from directory - Hot reload updates plugin without restart - Invalid plugins rejected with clear error messages - Conflict resolution works for overlapping patterns

Depends On: 5.1
Blocks: 5.3, 5.4

### 5.3 Plugin SDK & Documentation

Points: 10 | Assignee: Kimi Dev-3 | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 5.3.1 | SDK package | 2 | Publish phoenix-plugin-sdk package, base classes, utility functions, testing helpers, type stubs |
| 5.3.2 | CLI tooling | 2 | phoenix-plugin create — scaffold new plugin, phoenix-plugin validate — validate plugin, phoenix-plugin test — run plugin tests |
| 5.3.3 | Documentation | 2 | Plugin development guide, API reference, best practices, common patterns, troubleshooting guide |
| 5.3.4 | Testing utilities | 2 | Mock HTML fixtures for plugin tests, test HTTP client, test browser context, assertion helpers for scraper output |
| 5.3.5 | Example walkthrough | 2 | Step-by-step tutorial: create a plugin for a custom news site, from setup to deployment |

Acceptance Criteria: - SDK installable via pip install phoenix-plugin-sdk - CLI scaffolding creates working plugin template - Documentation covers all plugin development topics - Testing utilities reduce plugin test boilerplate by 80%

Depends On: 5.1, 5.2
Blocks: 5.5

### 5.4 Example Custom Scraper Plugin

Points: 12 | Assignee: Kimi Dev-3 | Priority: P2

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 5.4.1 | News site plugin | 3 | Complete example: scrape a news site (e.g., Hacker News), URL pattern matching, article extraction, comment extraction |
| 5.4.2 | E-commerce product plugin | 3 | Product scraper example: extract product title, price, description, images, reviews from a product page |
| 5.4.3 | Forum thread plugin | 3 | Forum scraper example: extract thread title, posts (author, content, timestamp), pagination handling |
| 5.4.4 | Integration tests | 3 | Full integration tests for each example plugin, recorded HTML fixtures, CI pipeline integration |

Acceptance Criteria: - All 3 example plugins pass integration tests - Each plugin demonstrates different capabilities - Plugins serve as reference implementations - Tests use recorded HTML fixtures (no live requests in CI)

Depends On: 5.2, 5.3, 2.16
Blocks: 5.5

### 5.5 Plugin Marketplace (Basic)

Points: 8 | Assignee: Kimi Dev-3 | Priority: P3

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 5.5.1 | Plugin manifest | 2 | plugin.yaml manifest: name, version, author, description, supported URLs, dependencies, documentation URL |
| 5.5.2 | Plugin directory | 2 | JSON/YAML registry of available plugins, search by domain/URL pattern, version history, popularity metrics |
| 5.5.3 | Installation | 2 | phoenix-plugin install <name> — download and install, dependency resolution, version pinning, uninstall support |
| 5.5.4 | Community guidelines | 2 | Contribution guide, code of conduct, review process, quality standards, security requirements |

Acceptance Criteria: - Plugin manifest validates against schema - Directory lists all available plugins - Install command works end-to-end - Contribution guide is complete

Depends On: 5.2, 5.3, 5.4
Blocks: —

### 5.6–5.10 Plugin Testing Framework

Points: 15 | Assignee: Kimi Dev-3 + QA | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 5.6 | Plugin unit test helpers | 3 | Mock HTML loader, mock HTTP responses, mock browser contexts, assertion helpers for extracted data, fixture generators |
| 5.7 | Plugin integration tests | 3 | Test full plugin pipeline: URL matching → scraping → normalization → output, test error handling, test fallback selectors |
| 5.8 | Plugin validation suite | 3 | Automated validation: URL patterns compile and match, selectors are valid, config schema validates, no circular dependencies |
| 5.9 | Plugin performance tests | 3 | Benchmark plugin execution time, memory usage test, concurrent execution test, resource cleanup verification |
| 5.10 | Plugin regression tests | 3 | Record HTML fixtures for plugin targets, detect when target site changes, alert on selector breakage, auto-suggest fixes |

Acceptance Criteria: - Unit test helpers reduce test code by 70% - Integration tests cover all plugin paths - Validation catches common plugin errors - Regression tests detect breakage within 24 hours

Depends On: 5.2, 5.3, 5.4
Blocks: —

## Phase 6 — Integration & Launch

Phase Lead: All Agents
Phase Goal: Integrate all components, validate end-to-end, launch
Phase Points: 55

### 6.1 Integration Testing — End to End

Points: 10 | Assignee: QA Lead | Priority: P0

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 6.1.1 | HTTP scraper E2E | 2 | Test HTTP scraper against 50 live URLs across all platforms, validate output schema, measure success rate and latency |
| 6.1.2 | Browser scraper E2E | 2 | Test browser scraper against 30 JS-heavy pages, validate stealth detection pass rate, measure memory usage |
| 6.1.3 | Cross-platform validation | 2 | Run all platform scrapers against live targets, validate data completeness, cross-reference fields |
| 6.1.4 | Error scenario testing | 2 | Test error paths: 404, 403, timeout, network error, invalid URL, empty response — verify graceful handling |
| 6.1.5 | Load testing | 2 | 100 concurrent scrapes, sustained load for 1 hour, memory leak detection, resource cleanup verification |

Acceptance Criteria: - E2E success rate > 95% across all platforms - All error scenarios handled gracefully - No memory leaks over 1-hour sustained load - All output validates against schema

Depends On: 2.1–2.24, 4.1–4.15
Blocks: 6.4

### 6.2 Documentation

Points: 10 | Assignee: All Dev | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 6.2.1 | API documentation | 2 | OpenAPI/Swagger spec for all endpoints, request/response examples, authentication guide, error code reference |
| 6.2.2 | Scraping guides | 2 | Per-platform scraping guides: Instagram, X/Twitter, TikTok, LinkedIn, Facebook, YouTube — with examples and limitations |
| 6.2.3 | Architecture docs | 2 | System architecture diagram, component interaction, data flow, deployment guide, configuration reference |
| 6.2.4 | Troubleshooting guide | 2 | Common errors and solutions, anti-bot mitigation guide, proxy configuration, debugging tips, FAQ |
| 6.2.5 | Changelog & versioning | 2 | Semantic versioning policy, changelog format, migration guides, deprecation policy |

Acceptance Criteria: - API docs complete with examples - All platforms have dedicated guide - Architecture docs include diagrams - Troubleshooting covers top 20 issues

Depends On: 1.1–1.12, 2.1–2.24, 4.1–4.15
Blocks: 6.4

### 6.3 Performance Optimization

Points: 8 | Assignee: Kimi Dev-1 + DevOps | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 6.3.1 | Profiling | 2 | CPU profiling of hot paths, memory profiling for leaks, async bottleneck identification, database query optimization |
| 6.3.2 | Caching layer | 2 | Redis-based response cache, selector result cache, robots.txt cache, DNS resolution cache |
| 6.3.3 | Concurrency tuning | 2 | Optimal connection pool sizing, optimal worker count per CPU, async task batching, connection keep-alive tuning |
| 6.3.4 | Resource optimization | 2 | Browser context reuse, image loading suppression, minimal resource fetching, garbage collection tuning |

Acceptance Criteria: - P95 latency < 5s for HTTP scrapes - P95 latency < 15s for browser scrapes - Memory usage stable over 24-hour run - Cache hit rate > 30% for repeated URLs

Depends On: 6.1
Blocks: 6.4

### 6.4 Production Deployment

Points: 10 | Assignee: Kimi DevOps | Priority: P0

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 6.4.1 | Production environment | 2 | Production Docker Compose / K8s manifests, environment-specific configuration, SSL certificates, domain setup |
| 6.4.2 | Monitoring setup | 2 | Production monitoring dashboard, alert channels (email/Slack), on-call rotation, incident response runbook |
| 6.4.3 | Backup verification | 2 | Automated backup testing, disaster recovery drill, data integrity verification, RTO/RPO validation |
| 6.4.4 | Security hardening | 2 | Production security review, penetration testing, dependency vulnerability scan, secrets audit |
| 6.4.5 | Launch checklist | 2 | Pre-launch verification: all tests pass, docs complete, monitoring active, backups verified, rollback plan ready |

Acceptance Criteria: - Production environment deployed and accessible - Monitoring active with all alerts configured - Backup recovery tested and documented - Security scan passes with no critical findings

Depends On: 4.9, 4.10, 6.1, 6.2, 6.3
Blocks: —

### 6.5–6.11 Post-Launch Operations

Points: 17 | Assignee: All | Priority: P1

| ID | Subtask | Points | Description |
| --- | --- | --- | --- |
| 6.5 | HTML fixture maintenance | 3 | Monthly refresh of recorded HTML fixtures, add fixtures for new page layouts, archive outdated fixtures |
| 6.6 | Selector health monitoring | 3 | Daily automated selector validation, health score dashboard, auto-alert on degradation, monthly selector review |
| 6.7 | Anti-bot adaptation | 2 | Monitor anti-bot landscape, update stealth techniques, rotate proxy strategies, browser patch management |
| 6.8 | Performance monitoring | 2 | Continuous performance tracking, latency trend analysis, capacity planning, scaling triggers |
| 6.9 | User feedback integration | 2 | Feedback collection mechanism, issue triage process, priority scoring, feedback-driven roadmap |
| 6.10 | Monthly reviews | 3 | Team retro on scraping challenges, selector breakage analysis, success rate trends, technical debt review |
| 6.11 | Quarterly planning | 2 | New platform evaluation, feature prioritization, technical debt paydown, infrastructure scaling |

Acceptance Criteria: - Fixtures refreshed within 7 days of layout changes - Selector health monitored daily - Anti-bot techniques updated monthly - User feedback reviewed weekly

Depends On: 6.4
Blocks: —

## Dependency Graph

PHASE 1: CORE ENGINE (Foundational — all other phases depend on this)
═══════════════════════════════════════════════════════════════════
1.1 HTTP Scraper ──────┬──► 1.7 Strategy Selector ────► 2.x All Platform Scrapers
1.2 HTML Parsing ──────┤                            ▲
1.3 CSS Selector ──────┤                            │
1.4 XPath Engine ──────┼──► 1.8 Output Normalizer ─┘
1.5 Regex Helpers ─────┤      ▲
1.6 Browser Scraper ───┘      │
1.9 Error/Retry ──────────────┤
1.10 Audit Logging ───────────┤
1.11 Pipeline Controller ─────┘
1.12 Regex Library ───────────► 2.12 YouTube, 2.x Social

                              PHASE 2: PLATFORM SCRAPERS
═══════════════════════════════════════════════════════════════════════════════
                              2.1 Instagram Posts ──► 2.2 Reels, 2.3 Profiles
                              2.4 X/Twitter Tweets ──► 2.5 Profiles
                              2.6 TikTok Videos ──► 2.7 Profiles
                              2.8 LinkedIn Posts ──► 2.9 Profiles
                              2.10 Facebook Posts ──► 2.11 Pages
                              2.12 YouTube Videos ──► 2.13 Transcripts, 2.14 Channels, 2.15 Comments
                              2.16 Generic Web ──► 2.17 Metadata
                              2.18–2.24 Pagination (shared by all)

                                                          PHASE 3: INTELLIGENCE
═════════════════════════════════════════════════════════════════════════════════════
                                                          3.1 Structure Analysis ──► 3.2 Fallback Chains
                                                          3.3 Content Classifier ──┤       │
                                                          3.4 Anti-Bot Detection ──┤       │
                                                                                  ▼       ▼
                                                          3.5 Auto Repair ◄──────────────┘
                                                          3.6 Adaptive Rate Limiting

PHASE 4: INFRASTRUCTURE
═══════════════════════════════════════════════════════════════════════════════════════════
4.1 Session Manager ──┬──► 4.3 Browser Pool ──► All browser scrapers
4.2 Proxy Mgmt ───────┤       ▲
4.4 Stealth Config ───┘       │
4.5 Rate Controller ──────────┤
4.6 HTML Archive ─────────────┤
4.7 Output Storage ───────────┤
4.8 Monitoring ───────────────┘
4.9 Docker ──► 4.10 CI/CD ──► 6.4 Deployment
4.11–4.15 Security

PHASE 5: PLUGIN SYSTEM
═════════════════════════════════════════════════════════════════════════
5.1 Interface ──► 5.2 Loader ──► 5.3 SDK ──► 5.4 Examples ──► 5.5 Marketplace
                                      │
                                      └──► 5.6–5.10 Testing Framework

PHASE 6: INTEGRATION & LAUNCH
═════════════════════════════════════════════════════════════════════════
All Phases 1–5 ──► 6.1 E2E Testing ──► 6.3 Performance ──► 6.4 Production
                   6.2 Documentation ──►           ▲            ▲
                                                   └────────────┘
                                            6.5–6.11 Post-Launch Ops

### Critical Path

1.1 HTTP Scraper → 1.2 HTML Parsing → 1.3 CSS Selector → 1.6 Browser Scraper
→ 1.7 Strategy Selector → 1.8 Output Normalizer → 1.11 Pipeline Controller
→ 2.1 Instagram / 2.4 X/Twitter / 2.12 YouTube / 2.16 Generic
→ 4.1 Session Manager / 4.2 Proxy / 4.3 Browser Pool / 4.5 Rate Controller
→ 6.1 E2E Testing → 6.4 Production Deployment

## Resource Loading

### Story Points by Agent

| Agent | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Dev-1 | 135 | — | 75 | — | — | 8 | 218 |
| Dev-2 | — | 85 | — | — | — | — | 85 |
| Dev-3 | — | 85 | — | — | 65 | — | 150 |
| DevOps | — | — | — | 100 | — | 20 | 120 |
| QA | — | — | — | — | — | 27 | 27 |

### Weekly Burndown Plan (8-Week Timeline)

| Week | Dev-1 | Dev-2 | Dev-3 | DevOps | QA | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 35 | 25 | 25 | 20 | — | 105 |
| 2 | 35 | 25 | 25 | 20 | — | 105 |
| 3 | 35 | 25 | 25 | 20 | — | 105 |
| 4 | 35 | 25 | 25 | 20 | 10 | 115 |
| 5 | 30 | 20 | 20 | 10 | 10 | 90 |
| 6 | 25 | 15 | 15 | 10 | 7 | 72 |
| 7 | 15 | 10 | 15 | — | — | 40 |
| 8 | 8 | — | — | — | — | 8 |

### Phase Timeline

Week:  1       2       3       4       5       6       7       8
       ├───────┤
       │  Phase 1: Core Engine (135 pts)  │
               ├───────────────────────────────┤
               │  Phase 2: Platform Scrapers (170 pts)  │
                       ├───────────────────────┤
                       │  Phase 3: Intelligence (75 pts)  │
       ├───────────────────────────────────────┤
       │  Phase 4: Infrastructure (100 pts)     │
                               ├───────────────┤
                               │  Phase 5: Plugins (65 pts)  │
                                       ├───────┤
                                       │ Phase 6: Integration (55 pts)│

## Risk Register

| ID | Risk | Probability | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R1 | Target site HTML structure changes breaking selectors | High | High | Smart fallback chains (3.2), auto-repair (3.5), selector regression tests (QA) | Dev-1 |
| R2 | Anti-bot measures block scraping | High | High | Stealth configuration (4.4), proxy rotation (4.2), adaptive rate limiting (3.6), browser automation | DevOps |
| R3 | Browser automation performance issues | Medium | High | Browser pool management (4.3), HTTP-first strategy (1.7), resource optimization (6.3) | DevOps |
| R4 | Legal/ethical compliance issues | Medium | High | robots.txt compliance (4.5), public-only scraping, rate limiting, ethical scraping policy | DevOps |
| R5 | Proxy failure/depletion | Medium | Medium | Health checking (4.2), failover handling, multiple proxy providers | DevOps |
| R6 | Memory leaks in long-running scraper | Medium | High | Browser context lifecycle (4.3), memory monitoring (4.8), periodic restarts | Dev-1 |
| R7 | Plugin API instability | Low | Medium | Semantic versioning, deprecation policy, comprehensive tests (5.6–5.10) | Dev-3 |
| R8 | Target site requires authentication | Medium | Medium | Cookie/session management (4.1), graceful degradation, public-only scope | Dev-2 |
| R9 | Concurrent scraping causes IP bans | Medium | High | Rate limiting (4.5), proxy rotation, per-domain concurrency limits | DevOps |
| R10 | HTML parsing performance on large pages | Low | Medium | lxml for speed, streaming parser for huge pages, size limits | Dev-1 |

## Document History

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | 2025-01-15 | System | Initial WBS with generic tasks |
| 2.0 | 2025-01-21 | System | Complete rewrite for pure scraping focus — 78 tasks, 520 points, 5 phases covering HTTP/browser scraping, social platform HTML scrapers, intelligence layer, infrastructure, and plugin system |